Solving Industrial Scheduling Problems
with Constraint Programming
Philippe Laborie
IBM Analytics, Decision Optimization

---
Outline
- Scheduling problems: from theory to practice
- CP extensions for scheduling
- Simplifying model design & problem resolution

---
Scheduling problems: from theory to practice
- Theory: e.g. RCPSP (Resource Constrained Project Scheduling)
  - Problem definition:
    - A set of n tasks A1,...,An with specified duration Di for task Ai
    - A set of precedence constraints between tasks (precedence graph)
    - A set of m resources R1,...,Rm with specified capacity Cj for resource Rj
    - Each task Ai requires some resources in a given quantity
    - Objective is to minimize project makespan
  - Classical benchmark: PSPLib = 30-120 tasks
a1
a3
a2
a6
a5
a4
a7
a8
R1
R2

---
Scheduling problems: from theory to practice
- Theory: e.g. RCPSP (Resource Constrained Project Scheduling)
  - From an academical point of view, this is a very generic problem that subsumes many other classical scheduling problems
RCPSP
Job-shop
Hybrid Flow-shop
Open-shop
Flow-shop

---
Scheduling problems: from theory to practice
- Some real scheduling applications
  - Aerospace: Project scheduling, Aircraft assembly, Assembly line configuration, Satellite communication & observation, Rover activities …
  - Energy & Utilities: Nuclear plant outage scheduling, Maintenance, Production planning …
  - Mining: Open pit mining ...
  - Logistics, Supply Chain: Vehicle routing, Bikes and car sharing …
  - Manufacturing: Production scheduling, Assembly lines, Factory configuration, Test scheduling …
  - Media & Communications: Advertizing & program scheduling, Event & personnel scheduling …
  - Travel & transportation: Airport scheduling (gates, landing, parking, …), Port scheduling (quay cranes ...), Train scheduling …
  - Health: Employee, Patient scheduling, Pharmaceutical products tests …
  - Agriculture: Crop scheduling (harvesting ...)
  - General audience: Personal schedule organizer, Theme park planner ...

---
Scheduling problems: from theory to practice
Practice: the problem looks like ...
this ...
or this ...

---
Scheduling problems: from theory to practice
- Practice: the problem is large
  - Typical problems are larger than 1000 activities
  - E.g. we solved a 1.000.000 tasks RCPSP-like problem for an aircraft manufacturer

---
Scheduling problems: from theory to practice
- Practice: the problem is complex
  - Heterogeneous types of decisions: start/end dates, resource allocation, mode selection, activity non-execution, activity durations, activity interruptions, resource quantities, producer/consumer matching, batch configuration, resource overconsumption, resource configuration, …
  - Complex resources: inventories, setup times and costs, calendars/shifts, moving resources, spatial constraints, synchronization constraints (e.g. conveyer belt), batch constraints
  - Complex activities: optional, interruptible, setups, maintenance, work breakdown structure
  - Complex objective function: earliness/tardiness, temporal preferences, resource related costs (many types!), most of the problems are multi-objectives

---
Scheduling problems: from theory to practice
- Practice: the problem is not well defined
  - Implicit constraints / objectives
  - Some aspects of the problem are critical, others can be:
    - Approximated
    - Relaxed
    - Over-constrained
    - Considered in a post-processing step
    - …
- Practice: the data is:
  - Hard to get (different data sources, confidentiality, …)
  - Uncertain / Imprecise / Incomplete / Incorrect
- Customers are expecting good solutions to their problem, they usually do not care about how the problem is modeled/solved

---
Scheduling problems: from theory to practice
Practice: mind the real gap
Real world
Model & Data
Modeling
minimize f(X)
subject to C(X)
gapS
Solve
solution X
Execution

---
Scheduling problems: from theory to practice
Practice: mind the real gap
  - “Essentially, all models are wrong, but some are useful” – G. Box
  - The real gap you must care about is gapM  gapS
Real world
Model & Data
Modeling
minimize f(X)
subject to C(X)
gapM
gapS
Solve
solution X
Execution

---
Scheduling problems: from theory to practice
Expressive modeling language
Robust & efficient
optimization
algorithm
Practice: mind the real gap
  - “Essentially, all models are wrong, but some are useful” – G. Box
  - The real gap you must care about is gapM  gapS
Real world
Model & Data
Modeling
minimize f(X)
subject to C(X)
gapM
gapS
Solve
Tools for simplifying model
design and resolution
solution X
Execution

---
CP extensions for scheduling
Extension of classical CSP with a new type of decision variable:
optional interval variable :
        Domain(x)  {}  { [s,e) | s,e, s≤e }
Introduction of mathematical notions such as sequences and functions to capture temporal dimension of scheduling problems
Absent interval
Interval of integers

---
CP extensions for scheduling
- In scheduling models, interval variables usually represent an interval of time during which some property hold (e.g. an activity executes) and whose end-points (start/end) are decision variables of the problem.
- Examples:
  - A sub-project in a project, a task in a sub-project (Work Breakdown Structure)
  - A batch of operations
  - The setup of a tool on a machine
  - The moving of an item by a transportation device
  - The utilization interval of a resource
- Idea of the model (and search) is to avoid the enumeration of start/end values (continuous time)

---
CP extensions for scheduling
- An interval variable can be optional meaning that it is a decision to have it present or absent in a solution.
- Examples:
  - Unperformed tasks and optional sub-projects
  - Alternative resources, modes or recipes for processing an order, each mode specifying a particular combination of operational resources
  - Operations that can be processed in different temporal modes (e.g. series or parallel)
  - Activities that can be performed in an alternative set of batches or shifts

---
CP extensions for scheduling
Example: RCPSP

---
CP extensions for scheduling
Example: Job-shop scheduling problem

---
CP extensions for scheduling
- Satellite Control Network scheduling problem [1]
- n communication tasks for Earth orbiting satellites must be scheduled on a total of 32 antennas spread across 13 ground-based tracking stations
- In the instances, n ranges from to 400 to 1300
- Objective: maximize the number of scheduled tasks
[1] Kramer & al.: Understanding Performance Trade-offs in Algorithms for Solving Oversubscribed Scheduling.

---
CP extensions for scheduling
Oppi,1
Oppi,2
Oppi,3
Oppi,4
OR
Alternative assignments
to stations  time windows
(opportunities)
Taski
Station 1
Station 2
Station 3

---
CP extensions for scheduling

---
Automatic Search
- Search algorithm is Complete
- Core CP techniques used as a building block:
  - Tree search (Depth First)
  - Constraint propagation
- But also:
  - Deterministic multicore parallelism
  - Model presolve
  - Algorithms portfolios
  - Machine learning
  - Restarting techniques
  - Large Neighborhood Search
  - No-good learning
  - Impact-based branching
  - Opportunistic probing
  - Dominance rules
  - LP-assisted heuristics
  - Randomization
  - Evolutionary algorithms

---
Automatic Search
- Very good performance results on academical problems
  - CP-AI-OR 2015:
  - Winner of the CP-2015 Industrial Modelling Challenge with a very simple model: csplib.org/Problems/prob073/models/model.mod.html
- More important: very good performance on industrial problems

---
Simplifying model design & problem resolution
Warnings
Warm start
User model
Internal model
Model analysis
Model presolve
OPL, C++, Java, .NET
Conflict
Model
Solution
CPO file
Search log
Automatic Solve
Conflict refiner

---
Tools: I/O format
- Objective:
  - Make it easier to understand the content of a model
  - Communicate a model to IBM support team regardless of the API used to build it (OPL, C++, Java, .NET)
- Structure of a .cpo file
  - Human readable
  - Flat (no cycle, forall statements)
  - No user defined data types
  - Internal information such as CPO version or platform used
  - Includes search parameter values
- Facilities
  - Export model before/instead of solve
  - Export model during solve (with current domains)
  - Import model instead of normal modeling

---
Tools: I/O format
// Interval-related variables:
"task(1)" = intervalVar(optional);
"task(1A)" = intervalVar(optional);
…
"opp({1,1,62})" = intervalVar(optional, start=62..intervalmax, end=0..99, size=25);
"opp({1A,1,32})" = intervalVar(optional, start=32..intervalmax, end=0..69, size=33);
…
// Objective:
maximize(sum([presenceOf("task(1)"), presenceOf("task(1A)"), …]));
…
// Constraints:
alternative("task(1)", ["opp({1,1,62})"], 1);
…
pulse("opp({3,1,58})", 1) + pulse("opp({1,1,62})", 1) + … <= 4;
…
parameters {
  LogVerbosity = Quiet;
}

---
Tools: model warnings
- Like a compiler, CP Optimizer can analyze the model and print some warnings
  - When there is something suspicious in the model
  - Regardless how the model was created (C++, OPL, …)
  - Including guilty part of the model in the cpo file format
  - Including source code line numbers (if known)
  - 3 levels of warnings, more than 50 types of warnings
satellite.cpo:2995:1: Warning: Constraint 'alternative': there is only one alternative interval variable.
        alternative("task(1)", ["opp({1,1,62})"], 1)
satellite.cpo:2996:1: Warning: Constraint 'alternative': there is only one alternative interval variable.
        alternative("task(1A)", ["opp({1A,1,32})"], 1)

---
Tools: model presolve
- Objective: automatically reformulate the model in order to speed-up its resolution
- Works on an internal representation of the model
- Different types of presolve:
  - Aggregation of basic constraints into global constraints
  - Constraint strengthening
  - Simplifications and factorizations

---
Tools: model presolve
- Examples of presolve rules
  - Common sub-expression elimination
  - Aggregation of x!=y cliques as allDifferent([x,y,...])
  - Precedence strengthening
    - If a and b cannot overlap and startsBeforeStart(a,b)
    - Then endsBeforeStart(a,b)
  - Precedence recognition
    - If endOf(a,-)  startOf(b,+)
    - Then endsBeforeStart(a,b)
    - Precedences are aggregated into a “time net” (STN) for faster and stronger propagation
  - 2-SAT clauses recognition
    - presenceOf(a)  presenceOf(b)
    - Such clauses are aggregated into a “logical net” for stronger propagation

---
Tools: search log
Objective: understand what happens during the automatic search
 ! -----------------------------------------------------------------------
 ! Maximization problem - 2980 variables, 853 constraints
 ! Workers = 2
 ! TimeLimit = 30
 ! Initial process time : 0.01s (0.00s extraction + 0.01s propagation)
 ! . Log search space : 4627.3 (before), 4627.3 (after)
 ! . Memory usage : 16.9 MB (before), 19.7 MB (after)
 ! Using parallel search with 2 workers.
 ! -----------------------------------------------------------------------
 ! Best Branches Non-fixed W Branch decision
 * 746 3945 0.79s 1 -
        746 4000 2924 1 on task("8")
        746 4000 2908 2 on opp({"186",2,66})
  …
 ! Time = 1.37s, Explored branches = 35832, Memory usage = 55.5 MB
 ! Best Branches Non-fixed W Branch decision
        818 12000 2920 1 on task("184")
  …
 ! -----------------------------------------------------------------------
 ! Search terminated by limit, 6 solutions found.
 ! Best objective : 826
 ! Number of branches : 709092
 ! Number of fails : 179648
 ! Total memory usage : 54.5 MB (52.9 MB CP Optimizer + 1.6 MB Concert)
 ! Time spent in solve : 30.03s (30.01s engine + 0.01s extraction)
 ! Search speed (br. / s) : 23625.4
 ! -----------------------------------------------------------------------
Problem
characteristics

---
Tools: search log
Objective: understand what happens during the automatic search
 ! -----------------------------------------------------------------------
 ! Maximization problem - 2980 variables, 853 constraints
 ! Workers = 2
 ! TimeLimit = 30
 ! Initial process time : 0.01s (0.00s extraction + 0.01s propagation)
 ! . Log search space : 4627.3 (before), 4627.3 (after)
 ! . Memory usage : 16.9 MB (before), 19.7 MB (after)
 ! Using parallel search with 2 workers.
 ! -----------------------------------------------------------------------
 ! Best Branches Non-fixed W Branch decision
 * 746 3945 0.79s 1 -
        746 4000 2924 1 on task("8")
        746 4000 2908 2 on opp({"186",2,66})
  …
 ! Time = 1.37s, Explored branches = 35832, Memory usage = 55.5 MB
 ! Best Branches Non-fixed W Branch decision
        818 12000 2920 1 on task("184")
  …
 ! -----------------------------------------------------------------------
 ! Search terminated by limit, 6 solutions found.
 ! Best objective : 826
 ! Number of branches : 709092
 ! Number of fails : 179648
 ! Total memory usage : 54.5 MB (52.9 MB CP Optimizer + 1.6 MB Concert)
 ! Time spent in solve : 30.03s (30.01s engine + 0.01s extraction)
 ! Search speed (br. / s) : 23625.4
 ! -----------------------------------------------------------------------
Modified
parameter values

---
Tools: search log
Objective: understand what happens during the automatic search
 ! -----------------------------------------------------------------------
 ! Maximization problem - 2980 variables, 853 constraints
 ! Workers = 2
 ! TimeLimit = 30
 ! Initial process time : 0.01s (0.00s extraction + 0.01s propagation)
 ! . Log search space : 4627.3 (before), 4627.3 (after)
 ! . Memory usage : 16.9 MB (before), 19.7 MB (after)
 ! Using parallel search with 2 workers.
 ! -----------------------------------------------------------------------
 ! Best Branches Non-fixed W Branch decision
 * 746 3945 0.79s 1 -
        746 4000 2924 1 on task("8")
        746 4000 2908 2 on opp({"186",2,66})
  …
 ! Time = 1.37s, Explored branches = 35832, Memory usage = 55.5 MB
 ! Best Branches Non-fixed W Branch decision
        818 12000 2920 1 on task("184")
  …
 ! -----------------------------------------------------------------------
 ! Search terminated by limit, 6 solutions found.
 ! Best objective : 826
 ! Number of branches : 709092
 ! Number of fails : 179648
 ! Total memory usage : 54.5 MB (52.9 MB CP Optimizer + 1.6 MB Concert)
 ! Time spent in solve : 30.03s (30.01s engine + 0.01s extraction)
 ! Search speed (br. / s) : 23625.4
 ! -----------------------------------------------------------------------
Root node
information

---
Tools: search log
Objective: understand what happens during the automatic search
 ! -----------------------------------------------------------------------
 ! Maximization problem - 2980 variables, 853 constraints
 ! Workers = 2
 ! TimeLimit = 30
 ! Initial process time : 0.01s (0.00s extraction + 0.01s propagation)
 ! . Log search space : 4627.3 (before), 4627.3 (after)
 ! . Memory usage : 16.9 MB (before), 19.7 MB (after)
 ! Using parallel search with 2 workers.
 ! -----------------------------------------------------------------------
 ! Best Branches Non-fixed W Branch decision
 * 746 3945 0.79s 1 -
        746 4000 2924 1 on task("8")
        746 4000 2908 2 on opp({"186",2,66})
  …
 ! Time = 1.37s, Explored branches = 35832, Memory usage = 55.5 MB
 ! Best Branches Non-fixed W Branch decision
        818 12000 2920 1 on task("184")
  …
 ! -----------------------------------------------------------------------
 ! Search terminated by limit, 6 solutions found.
 ! Best objective : 826
 ! Number of branches : 709092
 ! Number of fails : 179648
 ! Total memory usage : 54.5 MB (52.9 MB CP Optimizer + 1.6 MB Concert)
 ! Time spent in solve : 30.03s (30.01s engine + 0.01s extraction)
 ! Search speed (br. / s) : 23625.4
 ! -----------------------------------------------------------------------
New incumbent
solutions (time, worker)

---
Tools: search log
Objective: understand what happens during the automatic search
 ! -----------------------------------------------------------------------
 ! Maximization problem - 2980 variables, 853 constraints
 ! Workers = 2
 ! TimeLimit = 30
 ! Initial process time : 0.01s (0.00s extraction + 0.01s propagation)
 ! . Log search space : 4627.3 (before), 4627.3 (after)
 ! . Memory usage : 16.9 MB (before), 19.7 MB (after)
 ! Using parallel search with 2 workers.
 ! -----------------------------------------------------------------------
 ! Best Branches Non-fixed W Branch decision
 * 746 3945 0.79s 1 -
        746 4000 2924 1 on task("8")
        746 4000 2908 2 on opp({"186",2,66})
  …
 ! Time = 1.37s, Explored branches = 35832, Memory usage = 55.5 MB
 ! Best Branches Non-fixed W Branch decision
        818 12000 2920 1 on task("184")
  …
 ! -----------------------------------------------------------------------
 ! Search terminated by limit, 6 solutions found.
 ! Best objective : 826
 ! Number of branches : 709092
 ! Number of fails : 179648
 ! Total memory usage : 54.5 MB (52.9 MB CP Optimizer + 1.6 MB Concert)
 ! Time spent in solve : 30.03s (30.01s engine + 0.01s extraction)
 ! Search speed (br. / s) : 23625.4
 ! -----------------------------------------------------------------------
Periodical log
with fail information,
number of unfixed
variables, current decision

---
Tools: search log
Objective: understand what happens during the automatic search
 ! -----------------------------------------------------------------------
 ! Maximization problem - 2980 variables, 853 constraints
 ! Workers = 2
 ! TimeLimit = 30
 ! Initial process time : 0.01s (0.00s extraction + 0.01s propagation)
 ! . Log search space : 4627.3 (before), 4627.3 (after)
 ! . Memory usage : 16.9 MB (before), 19.7 MB (after)
 ! Using parallel search with 2 workers.
 ! -----------------------------------------------------------------------
 ! Best Branches Non-fixed W Branch decision
 * 746 3945 0.79s 1 -
        746 4000 2924 1 on task("8")
        746 4000 2908 2 on opp({"186",2,66})
  …
 ! Time = 1.37s, Explored branches = 35832, Memory usage = 55.5 MB
 ! Best Branches Non-fixed W Branch decision
        818 12000 2920 1 on task("184")
  …
 ! -----------------------------------------------------------------------
 ! Search terminated by limit, 6 solutions found.
 ! Best objective : 826
 ! Number of branches : 709092
 ! Number of fails : 179648
 ! Total memory usage : 54.5 MB (52.9 MB CP Optimizer + 1.6 MB Concert)
 ! Time spent in solve : 30.03s (30.01s engine + 0.01s extraction)
 ! Search speed (br. / s) : 23625.4
 ! -----------------------------------------------------------------------
Final information
with solution status
and search statistics

---
Tools: warm start
- Objective: Start search from a known (possibly incomplete) solution given by the user (warm start) in order to further improve it or to help to guide the engine towards a first feasible solution
- API: IloCP::setStartingPoint(IloSolution warmstart)
- Use cases:
  - Restart an interrupted search with the current incumbent
  - Start from an initial solution found by an available heuristic
  - Goal programming for multi-objective problems
  - When finding an initial solution is hard, solve an initial problem that maximizes constraint satisfaction and start from its solution
  - Successively solving similar problems (e.g. dynamic scheduling)
  - Hierarchical problem solving (e.g. planning → scheduling)

---
Tools: conflict refiner
- Objective: identify a reason for an inconsistency by providing a minimal infeasible subset of constraints for an infeasible model
- Use cases:
  - Model debugging (errors in model)
  - Data debugging (inconsistent data)
  - The model and data are correct, but the associated data represents a real-world conflict in the system being modeled
  - You create an infeasible model to test properties of (or extract information about) a similar model

---
Tools: conflict refiner

---
Tools: conflict refiner
  !----------------------------------------------------------------------------
 ! Satisfiability problem - 2,980 variables, 851 constraints
 ! Problem found infeasible at the root node
 ! ----------------------------------------------------------------------------
   ...
 ! ----------------------------------------------------------------------------
 ! Conflict refining - 851 constraints
 ! ----------------------------------------------------------------------------
 ! Iteration Number of constraints
 * 1 851
 * 2 426
  ...
 * 58 5
 * 59 5
 ! Conflict refining terminated
 ! ----------------------------------------------------------------------------
 ! Conflict status : Terminated normally, conflict found
 ! Conflict size : 5 constraints
 ! Number of iterations : 59
 ! Total memory usage : 13.3 MB
 ! Conflict computation time : 0.51s
 ! ----------------------------------------------------------------------------

---
Tools: conflict refiner
Conflict:
- There is not enough antennas to accommodate all 4 tasks on their time-window on ground station “LION” (3 antennas):
  - <134A,6,1232,19,1266>
  - <144, 6,1238,31,1272>
  - <146, 6,1228,22,1260>
  - <146A,6,1230,22,1262>
1228
1260
1230
1262
1232
1266
1238
1272
134A
144
146
146A

---
Simplifying model design & problem resolution
Warnings
Warm start
User model
Internal model
Model analysis
Model presolve
OPL, C++, Java, .NET
Conflict
Model
Solution
CPO file
Search log
Automatic Solve
Conflict refiner

---
From mathematical tools to real applications
Project
environment
Problem
definition
Data
Problem
decomposition
Optimization
technologies
Visualization
Interactivity
Development
tools